## README
Last Update | 2018-10-10
Author | Jocelyne Zarco, Jasmine Kwong, Jennifer Shin, Kevin Tran, Matthew Lebouvier
Email | jkwon045@ucr.edu, jzarc002@ucr.edu, jshin026@ucr.edu
Description | Instantly meet people near you. Discover new friends at a local bar or from the other side of the planet. Millions of people are connecting and meeting every day.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means by "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Minimize task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
7 | Registration | As an unregistered customer who is insterested in the app, I want to register an account so that I can login the app | 3 | 1
1 | Login/Logout | As a registered user, I want to login my account with user name and password, and logout my account to end the session | 1 | 2
2 | Contacts | As a user, I want to add a person into my contacts so that I can connect with my friends and also edit the contacts so that I can update their information | 4 | 3
4 | Profile | As a user, I want to edit my profile so that my contacts can view my information | 2 | 4
3 | Messaging | As a user, I want to message any one who is in my contacts who is also nearby me. | 8 | 5 | To be split
6 | Blocking | As a user, I want to block some contacts so that I will not recieve messages from them and they cannot view my profile | 6 | 6
5 | Notification | As a user, I want to receive notification when I get messages from someone | 6 | 7
9 | Settings | As a user, I want to customize how certain features appear and interact and change how I receive notifications.
8 | Searching | As a user, I want to search a contact in my contact list so that I can quickly find a person | 5 | 8
10 | Location Sharing | As a user, I want to be able to show my location when making certain posts. |  | 5
11 | Do Not Disturb | As a user, I want to be able to toggle notifications from this app. |  | 6
12 | Theming | As a user, I would like to be able to change the theming of the app. |  | 12
13 | Location Heat Map | As a user, I would like to be able to see where people congregate. |  | 13
| Total |  | 35

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Task 1: Set up working environment (all)
Task 2: Create home screen
Task 3: Set up firebase
Task 4: Registration
Task 5: Login

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | David Hoffman | Task 1: Login Page Design (John Li)
1
..

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 35 | 0 | 0 | 35 | 35
1 | 35 | 2 | 2 | 33 | 30.625
2 | 36 | 3 | 5 | 31 | 26.25
3 | 36 | 3 | 8 | 28 | 21.875
4 | 36 | 4 | 12 | 24 | 17.5
5 | 34 | 3 | 15 | 19 | 13.125
6 |  |  |  |  | 8.75
7 |  |  |  |  | 4.375
8 |  |  |  |  | 0